## Slide 1: GEELY CX11 EU ST – Organization
R&R of Vietnam validation team for Geely CX11 EU ST project Develop TC for CX11 base on new changes Verify OEM defects System test (Full validation) Exploratory Testing
Function Leader
Leaders
Month | 2020 |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
DCV TL | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
DCV Tester | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Total DCV | 0.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
FPT Senor | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
FPT Junior | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FPT_Total | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Total | 2.5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
New members
VN Test Team
Audio, Entertainment
Dat Nguyen
HMI M&D
Kien Vu
HMI M&D
Lan Vuong
HMI M&D, Telephony
Tuan Nguyen
HMI M&D, Infotainment Platform
Nam Ta
HMI M&D
Xen Le
HMI M&D
Ngoc Nguyen
Project Owner
Alex Won
Project Manager
Jin-hyun Park
HQ Test Team
Project Manager
Kevin We
Part Leader
Truong Dao
Test Leader
Bich Do

## Slide 2: GEELY CX11 EU ST – Project Progress – Test Result
)*100%
Chart: Pass Rate
| FV1 | FV2 | FV3 | FV4
CX11 EU | 0.92 | 0.94 | 0.91 | 0.95
CX11 20A | 0.99 | 0.99
Chart: Productivity (TCs/ Man-Day)
| Jul | Aug | Sep | Oct | Total (Acc.)
Actual (Acc.) | 69.2292
Target (Acc.) | 55
Actual (Monthly) | 59.4491 | 65.861 | 78.7826 | 69.7244
Target (Monthly) | 65 | 65 | 65 | 65
Chart: Defect Status (Accumulated)
| FV1 | FV2 | FV3 | FV4
Open | 20 | 39 | 64 | 95
Resolved | 19 | 32 | 49 | 61
Closed | 7 | 31 | 60 | 77
Total | 46 | 102 | 173 | 233
Chart: True-Defect Rate
| Jul | Aug | Sep | Oct
Actual (Acc.) | 1
Target (Acc.) | 0.95
Actual (Monthly) | 1 | 1 | 1 | 1
Target (Monthly) | 0.95 | 0.95 | 0.95 | 0.95
Notes: Test environment is more stable
Pass rate has increased
Tester run the same TCs with Aug, the same TCs for CX11 EU and CX11 20A -> Got used to those TCs.

## Slide 3: GEELY CX11 EU ST – Plan & Request
Monthly activities
Issue & Request
Activity of Oct | Oct’s actual result | Nov’s progress | Remark
Execute test FV4 for CX11 EU on IP739 (10/06~10/28) ~ 2516 TCs | - Completed 100% (2516/ 2516 TCs) on Oct 15th. Pass rate 95% | - Sanity test on IP740.04 (11/11~11/11) ~ 303 TCs - Sanity test on IP740.05 (11/12~11/13) ~ 303 TCs - Develop TCs for new changes | Done Sanity test
Investigate OEM defect (10/26 ~ 10/30) ~240 defects | - Completed 100% ( 240/ 240 defects) - 191/ 240 defects need creating TCs to cover defect content | - Verify OEM defects (11/06~11/09) ~ 38 defects Closed: 13 Reopened: 0 NT: 25 | 25 defects cannot verify due to poor test environment ( Do not have Rig, user profile, TEM, DTC, Navigation) or need to test on a real car.
Exploratory testing (10/16~10/23) | - 6 defects found. | - Exploratory Testing on IP740.05 for CX11 EU (11/09~11/10). 11 new defects found. - Exploratory Testing on IP740.05 (11/23~11/30) | 
No. | Description | Type | Cause / Request / Action Plan / Progress | PIC
1 | Cannot start create TCs base on new changes | Issue | The release note has not been delivered yet due to a delay from Development team. Mr. Park will send when he get it. | Mr. Jin- Hyun Park
2 | Long term validation and Resource plan | Request | Please share with us long term validation plan and resource plan for this project | Mr. Won

## Slide 5: GEELY CX11 EU ST – Effort Distribution
Total Effort Distribution
Chart: 
| Execute Test | Test Environment | Investigate RQ& Practice TCs | Exploratory Testing | Defect Management | Verify OEM/internal defects | Test management | Seminar | Day off
Sep | 0.21 | 0.02 | 0.4 | 0.01 | 0.08 | 0 | 0.06 | 0.1 | 0.12
Oct | 0.22 | 0.03 | 0.02 | 0.21 | 0.19 | 0.14 | 0.04 | 0.06 | 0.09
Notes: Pass rate:
CX11 EU: has increased from 90% (July) to 94% (Aug)
CX11 20A: has increased from 98% (July) to 100% (Aug)